## Gantt Chart
KickStart GANTT CHART
PROJECT TITLE | KickStart
PROJECT MANAGER | Name Surname
COMPANY NAME | IT Service Provider
DATE | 01/01/2025 to 04/06/2025
[7 empty] | Project Initiation | [9 empty] | Discovery Phase | [18 empty] | Design Phase | [21 empty] | Development Phase | [8 empty] | Testing Phase | [6 empty] | Deployment Phase | [7 empty] | Maintenance Phase
TASK | TASK | TASK | START | DUE | DURATION | PCT OF TASK | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12 |  |  |  |  | WEEKS 13-23 |  |  |  |  | WEEK 24-28 |  |  |  |  | WEEK 29 |  |  |  |  | WEEK 30 |  |  |  |  | WEEK 31 |  |  |  |  | WEEK 32
ID | TITLE | OWNER | DATE | DATE | IN DAYS | COMPLETE | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M
1 | Project Initiation
1.1 | Define project scope and create scope statement | Anna K. | 2025-01-01 | 2025-01-02 | 2 | 100%
1.1.1 | Stakeholder analysis | Ivan O. | 2025-01-03 | 2025-01-04 | 2 | 100%
1.2 | Create WBS project plan | Vira T. | 2025-01-05 | 2025-01-06 | 2 | 90%
1.3 | Assign roles and responsibilities | Anna K. | 2025-01-07 | 2025-01-08 | 2 | 40%
1.4 | Create project charter | Katerina P. | 2025-01-09 | 2025-01-11 | 3 | 70%
2 | Discovery Phase
2.1 | Conduct market research | Anna K. | 2025-01-12 | 2025-01-16 | 5 | 5%
2.2 | Gather requirements from stakeholders | Katerina P. | 2025-01-17 | 2025-01-22 | 6 | 30%
2.3 | Define user personas and user stories | Anna K. | 2025-01-23 | 2025-01-27 | 5 | 0%
2.4 | Perform competitor analysis | Katerina P. | 2025-01-28 | 2025-02-01 | 5 | 0%
3 | Design Phase
3.1 | Develop wireframes and prototypes | Vira T. | 2025-02-02 | 2025-02-09 | 8 | 0%
3.2 | Create visual design concepts | Anna K. | 2025-02-10 | 2025-02-16 | 7 | 0%
3.3 | Review and refine designs based on feedback | Katerina P. | 2025-02-17 | 2025-02-24 | 8 | 0%
4 | Development Phase
4.1 | Set up development environment | Anna K. | 2025-02-25 | 2025-03-04 | 8 | 0%
4.2 | Build front-end layout and Ul components | Katerina P. | 2025-03-05 | 2025-03-19 | 15 | 0%
4.3 | Develop back-end functionality | Vira T. | 2025-03-20 | 2025-04-04 | 16 | 0%
4.4 | Implement database structure | Anna K. | 2025-04-05 | 2025-04-12 | 8 | 0%
4.5 | Integrate third-party APls or services | Vira T. | 2025-04-13 | 2025-04-20 | 8 | 0%
5 | Testing Phase
5.1 | Conduct unit testing | Anna K. | 2025-04-21 | 2025-04-26 | 6 | 0%
5.2 | Perform integration testing | Katerina P. | 2025-04-27 | 2025-05-01 | 5 | 0%
5.3 | Execute user acceptance testing (UAT) | Anna K. | 2025-05-02 | 2025-05-06 | 5 | 0%
5.4 | Address and fix bugs and issues | Vira T. | 2025-05-07 | 2025-05-11 | 5 | 0%
6 | Deployment Phase
6.1 | Prepare for deployment | Katerina P. | 2025-05-12 | 2025-05-15 | 4 | 0%
6.2 | Migrate app to production environment | Ivan O. | 2025-05-16 | 2025-05-18 | 3 | 0%
6.3 | Perform final testing in live environment | Anna K. | 2025-05-19 | 2025-05-21 | 3 | 0%
6.4 | Launch website to public | Vira T. | 2025-05-22 | 2025-05-24 | 3 | 0%
7 | Maintenance Phase
7.1 | Monitor app performance | Katerina P. | 2025-05-25 | 2025-05-27 | 3 | 0%
7.2 | Address user feedback and bug reports | Anna K. | 2025-05-28 | 2025-05-30 | 3 | 0%
7.3 | Implement updates and improvements | Katerina P. | 2025-05-31 | 2025-06-02 | 3 | 0%
7.4 | Perform regular backups and security checks | Vira T. | 2025-06-03 | 2025-06-04 | 2 | 0%

## Calculations
Phase Durations (in Weeks) |  |  |  |  | Define project scope and create scope statement | 2025-01-01 | 2025-01-02
Phase | Duration (Weeks) | Start Week | End Week | Percentage | Stakeholder analysis | 2025-01-03 | 2025-01-04
Project Initiation | 2 weeks | Week 1 | Week 2 | 6.5% | Create WBS project plan | 2025-01-05 | 2025-01-06
Discovery Phase | 4 weeks | Week 3 | Week 6 | 12.8% | Assign roles and responsibilities | 2025-01-07 | 2025-01-08
Design Phase | 4 weeks | Week 7 | Week 10 | 14.5% | Create project charter | 2025-01-09 | 2025-01-11
Development Phase | 9 weeks | Week 11 | Week 19 | 35.7% | Conduct market research | 2025-01-12 | 2025-01-16
Testing Phase | 4 weeks | Week 20 | Week 23 | 14.5% | Gather requirements from stakeholders | 2025-01-17 | 2025-01-22
Deployment Phase | 3 weeks | Week 24 | Week 26 | 8.7% | Define user personas and user stories | 2025-01-23 | 2025-01-27
Maintenance Phase | 2 weeks | Week 27 | Week 28 | 6% | Perform competitor analysis | 2025-01-28 | 2025-02-01
[5 empty] | Develop wireframes and prototypes | 2025-02-02 | 2025-02-09
[5 empty] | Create visual design concepts | 2025-02-10 | 2025-02-16
Here is the duration of each phase in days: |  |  |  |  | Review and refine designs based on feedback | 2025-02-17 | 2025-02-24
[5 empty] | Set up development environment | 2025-02-25 | 2025-03-04
Initiation Phase: 10 days |  |  |  |  | Build front-end layout and UI components | 2025-03-05 | 2025-03-19
Discovery Phase: 19 days |  |  |  |  | Develop back-end functionality | 2025-03-20 | 2025-04-04
Design Phase: 22 days |  |  |  |  | Implement database structure | 2025-04-05 | 2025-04-12
Development Phase: 54 days |  |  |  |  | Integrate third-party APIs or services | 2025-04-13 | 2025-04-20
Testing Phase: 22 days |  |  |  |  | Conduct unit testing | 2025-04-21 | 2025-04-26
Deployment Phase: 13 days |  |  |  |  | Perform integration testing | 2025-04-27 | 2025-05-01
Maintenance Phase: 11 days |  |  |  |  | Execute user acceptance testing (UAT) | 2025-05-02 | 2025-05-06
[5 empty] | Address and fix bugs and issues | 2025-05-07 | 2025-05-11
[5 empty] | Prepare for deployment | 2025-05-12 | 2025-05-15
[5 empty] | Migrate app to production environment | 2025-05-16 | 2025-05-18
[5 empty] | Perform final testing in live environment | 2025-05-19 | 2025-05-21
[5 empty] | Launch website to public | 2025-05-22 | 2025-05-24
[5 empty] | Monitor app performance | 2025-05-25 | 2025-05-27
[5 empty] | Address user feedback and bug reports | 2025-05-28 | 2025-05-30
[5 empty] | Implement updates and improvements | 2025-05-31 | 2025-06-02
[5 empty] | Perform regular backups and security checks | 2025-06-03 | 2025-06-04